## INDEX
CONSTRUCTION COMMITTEE (CC) Data Collection Formats — Master Workbook
Institution: _________________________ CC Coordinator: _____________ A.Y.: _______ Version: _____
Form No. | Format / Form Title | Purpose / Usage | Frequency
── GOVERNANCE & ADMINISTRATION ──
CC-00 | Committee Composition & Members Register | Record CC members, engineers, architects & advisors | Annual
CC-NA | Meeting Notice, Agenda & Dispatch Record | Formal notice and agenda for CC meetings | Each Meeting
CC-AT | Attendance & Quorum Register | Confirm attendance and quorum | Each Meeting
CC-MM | Meeting Minutes & Resolutions | Record decisions, resolutions & directives | Each Meeting
CC-ATR | Action Taken Report | Track implementation of CC resolutions | Each Meeting
── POLICY & PLANNING ──
CC-01 | Construction Policy & Governance Framework | Document construction norms, approval authority & rules | Annual
CC-02 | Campus Master Plan & Development Register | Record campus master plan, zoning & future expansion | Annual / Per Review
CC-03 | Multi-Year Capital Works Plan | Plan all construction projects over 3–5 year horizon | Annual
CC-04 | Annual Construction Budget | Plan annual capital expenditure for construction | Annual
── PROJECT INITIATION ──
CC-05 | Construction Project Proposal Form | Submit project proposal for CC approval | Per Project
CC-06 | Project Register — All Active Projects | Consolidated register of all construction projects | Continuous
CC-07 | Feasibility & Site Assessment Report | Document feasibility study and site suitability | Per Project
CC-08 | Regulatory Approval Register | Track building permits, RERA, municipal approvals | Per Project
CC-09 | Design & Drawing Approval Register | Track architectural and structural drawing approvals | Per Design
CC-10 | Environmental Clearance Register | Track environmental impact assessment and clearance | Per Project
── TENDER & PROCUREMENT ──
CC-11 | Tender Notice & Publication Register | Publish and track tender notices for construction works | Per Tender
CC-12 | Tender Document Issue Register | Track tender documents issued to bidders | Per Tender
CC-13 | Bid Receipt & Opening Register | Record bids received and opening proceedings | Per Tender
CC-14 | Bid Evaluation & Comparative Register | Evaluate and compare bids — technical and financial | Per Tender
CC-15 | Tender Award & Work Order Register | Record tender award decisions and work order issue | Per Tender
CC-16 | Rate Contract Register | Manage rate contracts for standard construction items | Annual
CC-17 | Contractor Empanelment Register | Register pre-qualified / empanelled contractors | Annual
── CONTRACT MANAGEMENT ──
CC-18 | Construction Agreement Register | Register all signed construction contracts | Per Contract
CC-19 | Performance Bank Guarantee Register | Track PBG submitted by contractors | Per Contract
CC-20 | Retention Money Register | Track retention money deducted and released | Per Contract
CC-21 | Contract Amendment / Variation Register | Track scope changes, variations and amendments | Per Change
CC-22 | Subcontractor Register | Register approved subcontractors for each project | Per Project
── SITE MANAGEMENT ──
CC-23 | Site Establishment Register | Document site setup — office, store, utilities, hoarding | Per Project
CC-24 | Site Labour Register | Register all labourers — skilled, semi-skilled, unskilled | Daily
CC-25 | Machinery & Equipment on Site Register | Register all plant, machinery and equipment on site | Per Project
CC-26 | Material Inspection & Testing Register | Inspect and test materials before use — concrete, steel | Per Delivery/Test
CC-27 | Daily Progress Report | Record daily construction progress and status | Daily
CC-28 | Weekly Progress Report | Summarise weekly progress against schedule | Weekly
CC-29 | Site Instruction Register | Record site instructions issued by engineer-in-charge | Per Instruction
CC-30 | Non-Conformance Report (NCR) Register | Log quality non-conformances and corrective actions | Per NCR
── MEASUREMENT & PAYMENT ──
CC-31 | Measurement Book (MB) Register | Record detailed measurements of work done for billing | Per Billing Cycle
CC-32 | Running Account (RA) Bill Register | Process and track Running Account bills from contractors | Per Bill
CC-33 | Final Bill Register | Process and settle final bill on project completion | Per Project
CC-34 | Recovery & Deductions Register | Track advances, retention, penalties deducted from bills | Per Bill
CC-35 | Price Escalation / Variation Register | Track and process price escalation claims | Per Claim
── QUALITY ASSURANCE ──
CC-36 | Quality Control Plan Register | Document quality control plan for each project | Per Project
CC-37 | Concrete Mix Design & Testing Register | Track concrete mix design, cube testing and results | Per Pour
CC-38 | Steel / Reinforcement Testing Register | Track steel testing — tensile, bend, chemical tests | Per Delivery
CC-39 | Soil & Foundation Test Register | Document soil tests, bearing capacity and foundation data | Per Project
CC-40 | Third Party / Independent Quality Audit Reg. | Track third-party quality audits and compliance | Per Milestone
── SAFETY ON SITE ──
CC-41 | Site Safety Plan Register | Document site-specific safety plan for each project | Per Project
CC-42 | Safety Inspection & Checklist Register | Weekly safety inspection of construction site | Weekly
CC-43 | PPE Issue & Compliance Register | Track PPE issued to and worn by site workers | Daily
CC-44 | Accident & Near-Miss Register | Log all accidents and near-misses on site | Per Incident
CC-45 | Scaffold & Formwork Inspection Register | Inspect scaffolding and formwork before use | Per Use
── PROJECT COMPLETION ──
CC-46 | Milestone / Physical Progress Register | Track milestone-wise physical completion percentage | Monthly
CC-47 | Snag List / Defect Register | Document defects at practical completion | At Completion
CC-48 | Project Completion Certificate Register | Issue and register completion and handing-over certificates | Per Project
CC-49 | Defect Liability Period (DLP) Register | Track defects reported during DLP and rectification | DLP Period
CC-50 | Handing Over & Asset Register | Hand over completed assets to user departments | Per Handover
── MONITORING & REPORTING ──
CC-51 | CC KPI Dashboard | Track all construction KPIs — schedule, cost, quality | Monthly
CC-52 | CC Annual Report Compilation Form | Year-end report for Governing Body, Finance, NAAC | Annual
• CC = Construction Committee — oversight of all capital construction, renovation and civil works on campus.
• All construction works above ₹5 lakhs require open tender; ₹1–5L = limited tender; < ₹1L = quotation.
• Building plan approval from local municipal authority / development authority is mandatory before commencement.
• Concrete cube test: 1 set per 5m³ of concrete. Steel test: 1 sample per 10 MT delivery. Retain test certificates.
• Site safety: All labourers must wear PPE. No work at height without harness. No scaffolding without inspection.
• CC data feeds into: NAAC AQAR Criterion IV (Infrastructure), NIRF, Governing Body capital expenditure records.
• Measurement Book (MB) is a legal document — all entries must be in ink, no erasures. Corrections: strike-through.
• Defect Liability Period (DLP): minimum 12 months after completion. Retain PBG until DLP expires.
• Environmental clearance: projects > 20,000 m² built-up area require EIA and MoEFCC clearance.
• Progress photos mandatory at each milestone — date-stamped and geotagged where possible.

## CC-00 Composition
CC-00: CONSTRUCTION COMMITTEE — COMPOSITION REGISTER
Institution: _________________________ A.Y.: _______ Constituted on: _______ Order No.: _______
Sl. | Name | Designation | Role in CC | Expertise | Email / Phone | Term | Signature
1 |  | Principal / Director | Chairperson | CC Leadership & Final Approval
2 |  | Estate Officer / Senior Civil Engineer | CC Coordinator | Day-to-day Construction Oversight
3 |  | Project Manager / Civil Engineer (In-house) | Senior Civil Engineer | Technical Supervision
4 |  | Structural Engineer (In-house / Consultant) | Structural Engineer | Structural Design & Safety
5 |  | Architect (In-house / Consulting) | Architect | Design & Layout
6 |  | Electrical Engineer / MEP Specialist | Electrical Engineer | Electrical & Plumbing Works
7 |  | Quantity Surveyor / Cost Estimator | Quantity Surveyor | Measurement & Cost Control
8 |  | Finance Officer / Accounts Officer | Finance Officer | Budget, Bills & Payments
9 |  | Legal Advisor / Advocate | Legal Advisor | Contract & Legal Compliance
10 |  | Senior Faculty Member (Elected) | Faculty Rep – 1 | User Requirement Voice
11 |  | Senior Faculty Member (Elected) | Faculty Rep – 2 | User Requirement Voice
12 |  | Retired PWD / CPWD Engineer / Expert | External Expert – Civil | External Technical Advisory
13 |  | Safety In-charge / HSE Officer | Safety Officer | Site Safety Compliance
14 |  | IQAC In-charge | IQAC Coordinator (Ex-off.) | NAAC / Accreditation Compliance
15 |  | Governing Body / Trust Member | Governing Body Rep | Governance & Policy Oversight
CC meets monthly or more frequently during active construction. Legal Advisor must attend all tender award meetings. External Expert provides independent technical review for projects > ₹1 crore.

## CC-NA Notice & Agenda
CONSTRUCTION COMMITTEE: MEETING NOTICE & AGENDA
Meeting No.:
A.Y. / Quarter:
Date:
Time:
Venue:
Mode:
Notice by:
Notice Date:
AGENDA ITEMS
Item No. | Agenda Item | Lead | Duration (Min)
1 | Confirmation of minutes of previous CC meeting
2 | Action Taken Report on previous CC resolutions
3 | Active projects — monthly progress review (project-wise)
4 | New project proposals — feasibility and approval
5 | Regulatory approvals — building permits, clearances status
6 | Design and drawing approvals — pending review
7 | Tender proposals — floatation, opening, evaluation
8 | Tender awards — recommendation and approval
9 | Contract amendments / variation orders — review
10 | Quality issues — NCRs, material test failures, deviations
11 | Safety incidents — site accident/near-miss review
12 | Site labour compliance — PF, ESI, wage register
13 | Measurement book verification — bill approvals
14 | RA bill payments — pending and approved
15 | Project budget vs. expenditure — variance analysis
16 | Milestones — achieved and delayed analysis
17 | Snag list / DLP issues — rectification status
18 | Contractor performance review
19 | NAAC infrastructure data — construction evidence
20 | Any Other Matter with Permission of Chairperson (AOMPC)
DISPATCH RECORD
Sl. | Member Name & Role | Mode | Date & Acknowledgement

## CC-AT Attendance
CC: ATTENDANCE & QUORUM REGISTER
Meeting No.: _______ Date: _______ Total Strength: _______ Quorum Required (50%): _______
Sl. | Name | Role | Mode (Physical/VC) | Present (P/A) | Proxy (Y/N) | Proxy Holder | Signature
1 |  |  | Physical |  | N
2 |  |  | Physical |  | N
3 |  |  | Physical |  | N
4 |  |  | Physical |  | N
5 |  |  | Physical |  | N
6 |  |  | Physical |  | N
7 |  |  | Physical |  | N
8 |  |  | Physical |  | N
9 |  |  | Physical |  | N
10 |  |  | Physical |  | N
11 |  |  | Physical |  | N
12 |  |  | Physical |  | N
13 |  |  | Physical |  | N
14 |  |  | Physical |  | N
15 |  |  | Physical |  | N
16 |  |  | Physical |  | N
17 |  |  | Physical |  | N
QUORUM VERIFICATION
Total CC Members
Present (Physical)
Present (VC)
Total Effective
Quorum Required (50%)
Quorum Achieved?

## CC-MM Minutes
CC: MEETING MINUTES & RESOLUTIONS
Meeting No.: _______ Date: _______ Venue: _______ Chairperson: ___________________
DISCUSSION & RESOLUTIONS
Resolution No. | Discussion & Resolution | Responsible | Voting | Target Date | Status
CC/RES/001 |  |  |  |  | Pending
CC/RES/002 |  |  |  |  | Pending
CC/RES/003 |  |  |  |  | Pending
CC/RES/004 |  |  |  |  | Pending
CC/RES/005 |  |  |  |  | Pending
CC/RES/006 |  |  |  |  | Pending
CC/RES/007 |  |  |  |  | Pending
CC/RES/008 |  |  |  |  | Pending
CC/RES/009 |  |  |  |  | Pending
CC/RES/010 |  |  |  |  | Pending
CC/RES/011 |  |  |  |  | Pending
CC/RES/012 |  |  |  |  | Pending
CC/RES/013 |  |  |  |  | Pending
CC/RES/014 |  |  |  |  | Pending
Next Meeting: _______ Chairperson: ___________________ CC Coordinator: ___________________

## CC-ATR Action Report
CC: ACTION TAKEN REPORT (ATR)
Current Meeting No.: _______ Date: _______ Previous Meeting Ref.: _______
Resolution No. | Resolution / Decision | Action Required | Responsible | Target Date | Completion Date | Status
CC/RES/001 | [5 empty] | In Progress
CC/RES/002 | [5 empty] | In Progress
CC/RES/003 | [5 empty] | In Progress
CC/RES/004 | [5 empty] | In Progress
CC/RES/005 | [5 empty] | In Progress
CC/RES/006 | [5 empty] | In Progress
CC/RES/007 | [5 empty] | In Progress
CC/RES/008 | [5 empty] | In Progress
CC/RES/009 | [5 empty] | In Progress
CC/RES/010 | [5 empty] | In Progress
CC/RES/011 | [5 empty] | In Progress
CC/RES/012 | [5 empty] | In Progress
CC/RES/013 | [5 empty] | In Progress
CC/RES/014 | [5 empty] | In Progress
ATR SUMMARY
Total Resolutions Under Review
Implemented
In Progress
Pending
Deferred
Implementation Rate (%)

## CC-06 Project Register
CC-06: CONSTRUCTION PROJECT REGISTER — ALL ACTIVE & RECENT PROJECTS
Institution: _________________________ CC Coordinator: ___________________ Last Updated: _______
Project Ref. | Project Name / Description | Category | Estimated Cost (₹L) | Contract Amount (₹L) | Start Date | Planned Completion | Contractor | Physical Progress % | Financial Progress % | Status
PRJ/2023/001 |  | New Building — Academic | [7 empty] | Planning
PRJ/2023/002 |  | New Building — Hostel | [7 empty] | Design Stage
PRJ/2023/003 |  | New Building — Admin | [7 empty] | Tender Stage
PRJ/2023/004 |  | Renovation — Academic | [7 empty] | Under Construction
PRJ/2024/005 |  | Renovation — Lab | [7 empty] | Structural Complete
PRJ/2024/006 |  | Renovation — Hostel | [7 empty] | Finishing Stage
PRJ/2024/007 |  | Infrastructure — Road | [7 empty] | Practical Completion
PRJ/2024/008 |  | Infrastructure — Drainage | [7 empty] | DLP Period
PRJ/2025/009 |  | Infrastructure — Compound Wall | [7 empty] | Completed & Handed Over
PRJ/2025/010 |  | Extension / Addition | [7 empty] | On Hold
PRJ/2025/011 |  | Interior Works | [7 empty] | Cancelled
PRJ/2025/012 |  | Electrical Works | [7 empty] | Planning
PRJ/2026/013 |  | Civil Repair | [7 empty] | Design Stage
PRJ/2026/014 |  | Sports Facility | [7 empty] | Tender Stage
PRJ/2026/015 |  | Green Campus | [7 empty] | Under Construction
PRJ/2026/016 |  | New Building — Academic | [7 empty] | Structural Complete
PROJECT PORTFOLIO SUMMARY
Total Projects
Under Construction
Completed & Handed Over
On Hold / Cancelled
Total Contracted Value (₹L)
Projects Behind Schedule

## CC-05 Project Proposal Form
CC-05: CONSTRUCTION PROJECT PROPOSAL FORM
Proposal Ref.: CC/PROP/______/______ Submitted by: _______ Date: _______
SECTION A — PROJECT DETAILS
Project Title:
Project Category: | [ ] New Construction [ ] Renovation [ ] Extension [ ] Infrastructure [ ] Interior [ ] Other
Location on Campus:
Total Built-up Area (m²):
Number of Floors:
Justification / Need:
User Department(s):
Priority Level: | [ ] Critical — Immediate [ ] High — This A.Y. [ ] Medium — Next A.Y. [ ] Low — Future Plan
Academic / Operational Impact if delayed:
Environmental considerations:
SECTION B — COST ESTIMATE
Preliminary Cost Estimate (₹L): | Based on: CPWD DSR / State PWD SOR / Market rates
Plinth Area Rate (₹/m²):
Civil Works (₹L):
MEP / Electrical (₹L):
Finishing & Interior (₹L):
Contingency @ 5% (₹L):
Total Project Cost (₹L):
Funding Source: | [ ] Institutional Own Funds [ ] RUSA [ ] AICTE [ ] State Govt [ ] Loan [ ] CSR [ ] Other
Budget Year Allocation (₹L):
SECTION C — SCHEDULE
Proposed Project Start Date:
Target Completion Date:
Construction Duration (months):
Key Milestone 1 — Foundation:
Key Milestone 2 — Superstructure:
Key Milestone 3 — Roof / Slab:
Key Milestone 4 — Finishing:
SECTION D — REGULATORY REQUIREMENTS
Building Plan Approval Required? | [ ] Yes — Local Authority: _______ [ ] No (≤ threshold area)
Fire NOC Required? | [ ] Yes [ ] Not at this stage
Environmental Clearance Required? | [ ] Yes — EIA required (>20,000 m²) [ ] No
RERA Registration Required? | [ ] Yes — if for student/faculty housing [ ] No
Structural Stability Certificate: | [ ] Required (>15m height) [ ] Not required
SECTION E — CC APPROVAL
Technical Committee Recommendation: | [ ] Approved as proposed [ ] Approved with modifications [ ] Deferred [ ] Rejected
Finance Officer Confirmation (budget): | [ ] Budget available [ ] Pending allocation [ ] External funding required
CC Chairperson Decision: | [ ] Approved — Proceed to Design [ ] Approved — Proceed to Tender [ ] Deferred
Governing Body Approval (if > ₹50L): | [ ] Approved — Resolution No.: _______ [ ] Pending
Submitted by: ___________________ CC Coordinator: ___________________ Chairperson: ___________________ Date: ___________________

## CC-13-14 Bid Evaluation
CC-13 / CC-14: BID OPENING & COMPARATIVE EVALUATION REGISTER
Bid opening is a public process — date and time must be published in advance. All bids to be opened in presence of CC members and bidders. Comparative statement (L1 identification) mandatory before award.
Tender Ref.: _______ Project: _______ Opening Date: _______ Opening Time: _______ Venue: _______
Sl. | Contractor Name | Bid Security Deposited | Tech. Eligibility | Quoted Amount (₹L) | Discount Offered (%) | Final Amount (₹L) | Estimated Cost (₹L) | % Above / Below Est. | Technical Score | Ranking
1 |  | Y | Qualified
2 |  | Y | Qualified
3 |  | Y | Qualified
4 |  | Y | Qualified
5 |  | Y | Qualified
6 |  | Y | Qualified
7 |  | Y | Qualified
8 |  | Y | Qualified
9 |  | Y | Qualified
10 |  | Y | Qualified
BID SUMMARY & AWARD RECOMMENDATION
L1 (Lowest Qualifying) Bidder
L1 Quoted Amount (₹L)
L1 Amount vs. Estimated Cost (%)
Estimated Cost (₹L)
Recommended for Award
CC Award Decision | [5 empty] | [ ] Accept L1 [ ] Negotiate [ ] Re-tender [ ] Reject All
Witness 1: ___________________ Witness 2: ___________________ CC Coordinator: ___________________ Chairperson: ___________________ Date: ___________________

## CC-27 Daily Progress Report
CC-27: DAILY SITE PROGRESS REPORT (DPR)
Project: _______ Project Ref.: _______ Date: _______ Site Engineer: ___________________ Contractor: ___________________
SECTION A — SITE CONDITIONS
Weather Conditions: | [ ] Clear [ ] Cloudy [ ] Rain — Work Stopped [ ] Extreme Heat
Work Stoppages (if any):
Visitors to Site:
SECTION B — LABOUR ON SITE
Category | Contractor's Labour | Subcontractor Labour | Total
Skilled (Mason, Carpenter, Bar Bender)
Semi-skilled (Painter, Plumber)
Unskilled
Supervisory Staff
Total
SECTION C — WORK DONE TODAY
Activity | Location / Grid | Quantity Done Today | Cumulative Quantity Done
SECTION D — MATERIALS RECEIVED TODAY
Material | Supplier | Quantity Received | GRN / DC No.
SECTION E — ISSUES & SITE INSTRUCTIONS
Issues / Problems Encountered:
Site Instructions Issued:
Safety Observations:
Site Engineer: ___________________ Contractor's Rep: ___________________ Date: ___________________

## CC-30 NCR Register
CC-30: NON-CONFORMANCE REPORT (NCR) REGISTER
NCR = formal notice to contractor of non-conforming work. All NCRs must be actioned within 7 days. Unresolved NCRs held against contractor's bill. Repeat NCRs may attract penalty as per contract.
NCR Ref. | Project Ref. | Non-Conformance Description | Location | Date Issued | Contractor Response | Corrective Action | Verification Date | Status
NCR/0001 | PRJ/2024/001 | Concrete quality below specified grade | [5 empty] | Open
NCR/0002 | PRJ/2024/002 | Reinforcement spacing / cover non-conforming | [5 empty] | Open
NCR/0003 | PRJ/2024/003 | Waterproofing membrane not as specified | [5 empty] | Open
NCR/0004 | PRJ/2024/004 | Brickwork plumb / level deviation | [5 empty] | Open
NCR/0005 | PRJ/2024/005 | Plaster thickness / finish defect | [5 empty] | Open
NCR/0006 | PRJ/2024/006 | Flooring level / finish defect | [5 empty] | Open
NCR/0007 | PRJ/2024/007 | Window / door frame fixing defect | [5 empty] | Open
NCR/0008 | PRJ/2024/008 | Material substitution without approval | [5 empty] | Open
NCR/0009 | PRJ/2025/009 | Unsafe scaffolding / formwork | [5 empty] | Open
NCR/0010 | PRJ/2025/010 | Labour non-compliance (no PPE) | [5 empty] | Open
NCR/0011 | PRJ/2025/011 | Drawing deviation without approval | [5 empty] | Open
NCR/0012 | PRJ/2025/012 | Curing period not maintained | [5 empty] | Open
NCR/0013 | PRJ/2025/013 | Concrete quality below specified grade | [5 empty] | Open
NCR/0014 | PRJ/2025/014 | Reinforcement spacing / cover non-conforming | [5 empty] | Open
NCR/0015 | PRJ/2025/015 | Waterproofing membrane not as specified | [5 empty] | Open
NCR/0016 | PRJ/2025/016 | Brickwork plumb / level deviation | [5 empty] | Open
NCR STATISTICS
Total NCRs Issued
Open NCRs
Closed / Resolved NCRs
Repeat Non-conformances
NCRs leading to Bill Deduction
Average Resolution Time (days)

## CC-37 Concrete Testing
CC-37: CONCRETE MIX DESIGN & CUBE TEST REGISTER
IS 456:2000 requirement: Minimum 1 set of 3 cubes per 5 m³ of concrete or per day's pour (whichever more). 7-day target: 70% of 28-day strength. 28-day result ≥ characteristic strength = PASS. Retain certificates.
Test Ref. | Project / Location | Date of Pour | Grade of Concrete | Volume Poured (m³) | Slump (mm) | Cube 7-Day Strength (N/mm²) | Cube 28-Day Strength (N/mm²) | Required Strength (N/mm²) | Result
CT/0001 |  |  | M15 |  |  |  |  | 15
CT/0002 |  |  | M20 |  |  |  |  | 20
CT/0003 |  |  | M25 |  |  |  |  | 25
CT/0004 |  |  | M30 |  |  |  |  | 30
CT/0005 |  |  | M35 |  |  |  |  | 35
CT/0006 |  |  | M40 |  |  |  |  | 40
CT/0007 |  |  | M15 |  |  |  |  | 15
CT/0008 |  |  | M20 |  |  |  |  | 20
CT/0009 |  |  | M25 |  |  |  |  | 25
CT/0010 |  |  | M30 |  |  |  |  | 30
CT/0011 |  |  | M35 |  |  |  |  | 35
CT/0012 |  |  | M40 |  |  |  |  | 40
CT/0013 |  |  | M15 |  |  |  |  | 15
CT/0014 |  |  | M20 |  |  |  |  | 20
CT/0015 |  |  | M25 |  |  |  |  | 25
CT/0016 |  |  | M30 |  |  |  |  | 30
CT/0017 |  |  | M35 |  |  |  |  | 35
CT/0018 |  |  | M40 |  |  |  |  | 40
CT/0019 |  |  | M15 |  |  |  |  | 15
CT/0020 |  |  | M20 |  |  |  |  | 20
CT/0021 |  |  | M25 |  |  |  |  | 25
CT/0022 |  |  | M30 |  |  |  |  | 30
CONCRETE QUALITY SUMMARY
Total Cube Sets Tested
PASS Results
FAIL Results — NCR Required
Pass Rate (%)
Average 28-Day Strength (N/mm²)
Cubes with < 70% at 7 days

## CC-42 Site Safety Checklist
CC-42: CONSTRUCTION SITE SAFETY INSPECTION CHECKLIST
Weekly safety inspection mandatory. Any safety violation = STOP WORK ORDER for that activity until rectified. Building & Other Construction Workers Act 1996 / IS 7969 applies.
Project: _______ Date: _______ Inspector: ___________________ Contractor Rep Present: ___________________
Sl. | Safety Parameter | Standard / Requirement | Rating (1–5) | Compliant (Y/N) | Observations | Action Required
A. PERSONAL PROTECTIVE EQUIPMENT (PPE)
1 | All workers wearing safety helmet (hard hat) | IS 2925 — mandatory on all construction sites |  | Y
2 | Safety shoes / gumboots worn | No slippers or bare feet on site |  | Y
3 | Safety harness worn at height (>2m) | IS 3521 — mandatory at height |  | Y
4 | High-visibility vest worn by supervisors | Fluorescent vest — all supervisors |  | Y
5 | Gloves worn for material handling | Leather / rubber gloves as appropriate |  | Y
6 | Ear protection in noisy areas | Earmuffs / earplugs near machinery |  | Y
7 | Dust mask in dusty areas | N95 or equivalent for dusty operations |  | Y
B. SCAFFOLDING & WORK AT HEIGHT
1 | Scaffold inspected and certified before use | Inspection tag visible on scaffold |  | Y
2 | Scaffold base plates and sole boards in place | No scaffolding erected on soft ground without base |  | Y
3 | Guard rails on all open edges (>2m height) | Top rail 900-1100mm, mid-rail 450-550mm |  | Y
4 | Toe boards fitted on scaffold platforms | 150mm toe board to prevent tools falling |  | Y
5 | Ladder properly secured and extends 1m above platform | 75° angle; tied at top |  | Y
6 | No overloading of scaffold platforms | Do not exceed rated SWL (Safe Working Load) |  | Y
C. EXCAVATION & TRENCHING
1 | Excavation edges shored or battered at safe angle | Sides battered ≥45° or shored for depth > 1.5m |  | Y
2 | Barricades and warning signs around excavation | Full perimeter barricading with warning tape |  | Y
3 | No material stacked within 1m of excavation edge | Materials stored away from trench edge |  | Y
4 | Means of egress every 8m in trenches | Ladders / steps every 8 metres |  | Y
5 | Excavation inspected daily by supervisor | Inspection record maintained |  | Y
D. ELECTRICAL SAFETY
1 | Temporary electrical panel properly erected | Metal enclosure; ELCB/RCCB fitted |  | Y
2 | All cables insulated — no open/damaged cables | No bare wires or taped joints on ground |  | Y
3 | Only licensed electricians working on electrical | Licence visible on site |  | Y
4 | Extension cords not used as permanent wiring | No daisy-chaining of extension cords |  | Y
5 | No work near overhead power lines | Minimum 3m clearance maintained |  | Y
E. MATERIAL STORAGE & HOUSEKEEPING
1 | Materials stacked safely and not excessively high | Max stack height: 1.5m for bricks; 3m for steel |  | Y
2 | Walkways and access routes clear of obstruction | All pathways kept clear at all times |  | Y
3 | Waste / debris removed regularly | Daily clearing of construction debris |  | Y
4 | Cement bags stored on pallets, covered | No cement directly on ground |  | Y
5 | First aid kit stocked and accessible | Stocked kit at site office; notice board |  | Y
6 | Fire extinguisher present and charged | At least 1 per 200 m² of work area |  | Y
Safety Inspector: ___________________ Contractor Safety Officer: ___________________ CC Coordinator: ___________________ Date: ___________________

## CC-32 RA Bill Register
CC-32: RUNNING ACCOUNT (RA) BILL REGISTER
Project Ref.: _______ Contractor: ___________________ Contract Amount: ₹ _______ L CC Coordinator: ___________________
Bill No. | Bill Description / Milestone | MB Ref. | Work Done Value (₹L) | Cumulative Work Done (₹L) | Less Retention @5% (₹L) | Less Advance Recovery (₹L) | Less Penalty (₹L) | Net Payable (₹L) | Payment Status
RA-01 | [8 empty] | Pending
RA-02 | [8 empty] | Pending
RA-03 | [8 empty] | Pending
RA-04 | [8 empty] | Pending
RA-05 | [8 empty] | Pending
RA-06 | [8 empty] | Pending
RA-07 | [8 empty] | Pending
RA-08 | [8 empty] | Pending
RA-09 | [8 empty] | Pending
RA-10 | [8 empty] | Pending
RA-11 | [8 empty] | Pending
RA-12 | [8 empty] | Pending
TOTAL (All Bills)
PAYMENT SUMMARY
Total Bills Submitted
Total Work Done Value (₹L)
Total Retention Deducted (₹L)
Total Net Paid (₹L)
Balance to Complete (₹L)
% of Contract Value Billed

## CC-46 Milestone Progress
CC-46: PROJECT MILESTONE & PHYSICAL PROGRESS REGISTER
Project Ref.: _______ Project Name: _______ Contract Duration: _______ CC Coordinator: ___________________
Milestone No. | Milestone Description | Planned Start | Planned Completion | Actual Start | Actual Completion | Physical Progress % | % of Contract Value | Delay (Days) | Status
1 | Site Establishment & Mob.
2 | Substructure — Excavation & Foundation
3 | Substructure — Plinth Beam
4 | Superstructure — Columns (All Floors)
5 | Superstructure — Beams & Slabs
6 | Staircase & Terrace Slab
7 | Brick / Block Work (All Floors)
8 | Plastering — Internal & External
9 | MEP — Conduit & Plumbing Rough-in
10 | Flooring & Tiling
11 | Doors, Windows, Frames & Glazing
12 | MEP — Finishing & Fixtures
13 | Painting — Internal & External
14 | External Development & Roads
15 | Handing Over / Practical Completion
PROJECT PROGRESS SUMMARY
Total Milestones
Completed
In Progress
Not Started
Milestones with Delay
Overall Physical Progress (%)

## CC-49 DLP Register
CC-49: DEFECT LIABILITY PERIOD (DLP) REGISTER
DLP: Minimum 12 months from practical completion. All defects reported during DLP must be rectified by contractor at no cost. Retain Performance Bank Guarantee (PBG) until DLP expires and final clearance given.
Defect Ref. | Project Ref. | Defect Description | Location | Date Reported | Date Notified to Contractor | Rectification Deadline | Date Rectified | Status
DLP/0001 | PRJ/2024/001 | Roof leakage | [5 empty] | Open
DLP/0002 | PRJ/2024/002 | Seepage / dampness in walls | [5 empty] | Open
DLP/0003 | PRJ/2024/003 | Flooring crack / settlement | [5 empty] | Open
DLP/0004 | PRJ/2024/004 | Plaster cracks | [5 empty] | Open
DLP/0005 | PRJ/2024/005 | Window / door frame gap | [5 empty] | Open
DLP/0006 | PRJ/2024/006 | Paint peeling / blistering | [5 empty] | Open
DLP/0007 | PRJ/2024/007 | Plumbing leakage | [5 empty] | Open
DLP/0008 | PRJ/2024/008 | Electrical fault | [5 empty] | Open
DLP/0009 | PRJ/2025/009 | Tile debonding | [5 empty] | Open
DLP/0010 | PRJ/2025/010 | Drainage blockage | [5 empty] | Open
DLP/0011 | PRJ/2025/011 | Structural crack (alert — immediate action) | [5 empty] | Open
DLP/0012 | PRJ/2025/012 | Finishing defect | [5 empty] | Open
DLP/0013 | PRJ/2025/013 | Roof leakage | [5 empty] | Open
DLP/0014 | PRJ/2025/014 | Seepage / dampness in walls | [5 empty] | Open
DLP/0015 | PRJ/2025/015 | Flooring crack / settlement | [5 empty] | Open
DLP/0016 | PRJ/2025/016 | Plaster cracks | [5 empty] | Open
DLP STATISTICS
Total Defects Reported
Rectified by Contractor
Open — Pending Rectification
Overdue (Beyond Deadline)
Structural Cracks (Critical)
PBG Released |  |  |  | [ ] Yes — Date: _______ [ ] No — Pending DLP Clearance

## CC-44 Accident Register
CC-44: SITE ACCIDENT & NEAR-MISS REGISTER
Fatal accidents: Report to police, Labour Department and BOCW (Building & Other Construction Workers) authority within 24 hours. Serious injury: Report to Labour Inspector. Preserve site evidence. ESIC/WC Act applies.
Incident Ref. | Project Ref. | Nature of Incident | Date & Time | Location | Person Involved | Injury Type | Authority Informed | Root Cause & Action Taken
ACC/0001 | PRJ/2024/001 | Fall from height — scaffolding
ACC/0002 | PRJ/2024/002 | Fall from height — ladder
ACC/0003 | PRJ/2024/003 | Hit by falling object
ACC/0004 | PRJ/2024/004 | Electrocution — minor
ACC/0005 | PRJ/2024/005 | Electrical shock — serious
ACC/0006 | PRJ/2024/006 | Cut / laceration — hand tool
ACC/0007 | PRJ/2024/007 | Crush injury — machinery
ACC/0008 | PRJ/2025/008 | Overexertion / back injury
ACC/0009 | PRJ/2025/009 | Eye injury — dust/debris
ACC/0010 | PRJ/2025/010 | Near-miss — no injury
ACC/0011 | PRJ/2025/011 | Chemical / dust exposure
ACC/0012 | PRJ/2025/012 | Structural collapse — partial
ACC/0013 | PRJ/2025/013 | Fall from height — scaffolding
ACC/0014 | PRJ/2025/014 | Fall from height — ladder
ACCIDENT STATISTICS
Total Incidents
Near-Misses
Minor Injuries
Serious Injuries
Fatal Accidents
Incident Rate (per 100 workers)

## CC-51 KPI Dashboard
CC-51: CONSTRUCTION COMMITTEE KPI DASHBOARD
Quarter: _______ A.Y.: _______ CC Coordinator: ___________________ Date: _______
PROJECT SCHEDULE KPIs
Sl. | Key Performance Indicator | Unit | Target | Prev. Quarter Actual | Current Quarter Actual | Status | Action Required
1 | Projects completed on schedule (% of active) | % on time | ≥80% |  |  | On Track
2 | Average schedule delay (days) | Days | < 30 days avg. |  |  | On Track
3 | Milestones achieved on time (%) | % on time | ≥75% |  |  | On Track
4 | Projects with approved time extension | No. | Tracked |  |  | On Track
5 | Projects with force majeure delays | No. | Tracked |  |  | On Track
COST & BUDGET KPIs
Sl. | Key Performance Indicator | Unit | Target | Prev. Quarter Actual | Current Quarter Actual | Status | Action Required
1 | Projects within approved budget (%) | % within budget | ≥85% |  |  | On Track
2 | Average cost overrun (% above contract) | % overrun | < 10% |  |  | On Track
3 | RA bill payment within 28 days (%) | % on time | ≥90% |  |  | On Track
4 | Retention money as % of total bills | % retention | ≤5% |  |  | On Track
5 | Capital expenditure vs. annual plan (%) | % utilised | 85–100% |  |  | On Track
6 | Total variation orders (% of contract value) | % variation | < 15% |  |  | On Track
QUALITY KPIs
Sl. | Key Performance Indicator | Unit | Target | Prev. Quarter Actual | Current Quarter Actual | Status | Action Required
1 | Concrete cube test pass rate (%) | % pass | ≥95% |  |  | On Track
2 | NCRs raised per month | No. | Tracked — decreasing |  |  | On Track
3 | NCRs closed within 7 days (%) | % on time | ≥90% |  |  | On Track
4 | Third party quality audit score | Score /100 | ≥75 |  |  | On Track
5 | DLP defects per project (avg) | No. | < 5 per project |  |  | On Track
SAFETY KPIs
Sl. | Key Performance Indicator | Unit | Target | Prev. Quarter Actual | Current Quarter Actual | Status | Action Required
1 | Lost Time Injury (LTI) incidents per month | No. | 0 target |  |  | On Track
2 | Near-miss incidents reported per month | No. | Tracked (reporting culture) |  |  | On Track
3 | Weekly safety inspection compliance (%) | % completed | 100% |  |  | On Track
4 | PPE compliance on site (% of workers) | % compliant | ≥95% |  |  | On Track
5 | Safety training for site workers (%) | % trained | 100% |  |  | On Track
COMPLIANCE & GOVERNANCE KPIs
Sl. | Key Performance Indicator | Unit | Target | Prev. Quarter Actual | Current Quarter Actual | Status | Action Required
1 | Regulatory approvals obtained before start | % projects | 100% |  |  | On Track
2 | Tender process as per prescribed procedure | % compliant | 100% |  |  | On Track
3 | Contractor labour compliance (PF/ESI/wage) | Y/N | Yes — all sites |  |  | On Track
4 | NAAC infrastructure data compiled | Y/N | Yes annually |  |  | On Track
5 | CC meetings held (monthly) | No. per quarter | ≥3 |  |  | On Track

## CC-52 Annual Report
CC-52: CONSTRUCTION COMMITTEE ANNUAL REPORT COMPILATION FORM
A.Y.: _______ CC Coordinator: ___________________ Submitted to: Governing Body / Finance / IQAC Date: _______
SECTION 1 — PROJECT PORTFOLIO
Sl. | Performance Metric | Unit | Current A.Y. | Previous A.Y. | Growth % | Target Next Year
1 | Total active construction projects | No.
2 | New projects initiated this A.Y. | No.
3 | Projects completed this A.Y. | No.
4 | Total contracted value — active projects (₹L) | ₹L
5 | Total expenditure — construction (₹L) | ₹L
6 | Area constructed / renovated (m²) | m²
SECTION 2 — SCHEDULE & COST
Sl. | Performance Metric | Unit | Current A.Y. | Previous A.Y. | Growth % | Target Next Year
1 | Projects completed on schedule (%) | % on time
2 | Average schedule delay (days) | Days
3 | Projects within budget (%) | % within budget
4 | Average cost overrun (%) | % overrun
5 | Total variation orders value (₹L) | ₹L
6 | RA bills paid within 28 days (%) | % on time
SECTION 3 — QUALITY & SAFETY
Sl. | Performance Metric | Unit | Current A.Y. | Previous A.Y. | Growth % | Target Next Year
1 | Concrete cube tests conducted | No.
2 | Cube test pass rate (%) | % pass
3 | Total NCRs raised | No.
4 | NCRs closed within 7 days (%) | % on time
5 | LTI (Lost Time Injury) incidents | No.
6 | Safety training sessions conducted | No.
SECTION 4 — COMPLIANCE
Sl. | Performance Metric | Unit | Current A.Y. | Previous A.Y. | Growth % | Target Next Year
1 | Projects with all regulatory approvals | % compliant
2 | Tender process compliance (%) | % compliant
3 | DLP defects reported (all projects) | No.
4 | DLP defects rectified (%) | % rectified
5 | Third-party quality audits conducted | No.
6 | NAAC data submitted | Y/N
Annual Report submitted to: Governing Body (capital expenditure approval), Finance Committee, IQAC (NAAC AQAR Criterion IV — Infrastructure), External Auditors. Measurement Books and Bills to be retained permanently as legal documents.
CC Coordinator: ___________________ Senior Civil Engineer: ___________________ Chairperson (Principal): ___________________ Date: ___________________